Project Planning Phase

Project Planning  (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 08/03/2026 |
| --- | --- |
| Team ID | SWTID-2026-1942 |
| Project Name | Product inventory management system |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Product initialisation | USN-1 | As a developer, I want to initialize the Node.js project and configure the Express server so that backend APIs can be developed. | 5 | High | Afrin roja |
| Sprint-1 | Database configuration | USN-2 | As a developer, I want to connect MongoDB Atlas and create the database structure so that product data can be stored securely. | 5 | High | Ayisha |
| Sprint-1 | User Model creation | USN-3 | As a developer, I want to create a user schema with password hashing so that user information is stored securely. | 8 | High | Nowsheen fathima |
| Sprint-2 | USER Authentication system | USN-4 | As a user, I want to register and login to the system so that I can securely access my account. | 8 | High | Sameena afrin |
| Sprint-2 | Authentication Middleware | USN-5 | As a developer, I want to create JWT verification middleware so that protected routes are secured. | 5 | High | Afrin roja |
| Sprint-2 | Product Model design | USN-6 | As a developer, I want to design a product schema linked with userId so that each user can manage their own products. | 5 | High | Ayisha |
| Sprint-3 | Product management | USN-7 | As a user, I want to add, update, delete and view products so that I can manage my inventory efficiently. | 13 | High | Nowsheen Fathima |
| Sprint-3 | Product search | USN-8 | As a user, I want to add, update, delete and view products so that I can manage my inventory efficiently. | 6 | Medium | Sameena afrin |
| Sprint-3 | Authorization Logic | USN-9 | As a developer, I want to ensure users can access only their own products so that data privacy is maintained. | 5 | High | Afrin roja |
| Sprint-4 | Error Handling | USN-10 | As a developer, I want to implement centralized error handling so that system errors are handled properly. | 5 | Medium | Ayisha |
| Sprint-4 | API Testing | USN-11 | As a tester, I want to test APIs using Postman so that all functionalities work correctly. | 5 | Medium | Sameena afrin |
| Sprint-4 | Backend Optimization | USN-12 | As a developer, I want to optimize API performance and implement validation checks so that the system works efficiently. | 5 | Medium | Nowsheen Fathima |

Project Tracker, Velocity & Burndown Chart:

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 18 | 5 Days | 17 Feb 2026 | 21 Feb 2026 | 18 | 21 Feb 2026 |
| Sprint-2 | 18 | 5 Days | 22 Feb 2026 | 26 Feb 2026 | 18 | 26 Feb 2026 |
| Sprint-3 | 23 | 5 Days | 27 Feb 2026 | 3 Mar 2026 | 23 | 3 Mar 2026 |
| Sprint-4 | 15 | 4 Days | 4 Mar 2026 | 8 Mar 2026 | 15 | 8 Mar 2026 |